## Stakeholder Register
Project: | Digital transformation for Starlight Medical Center |  |  |  | Stakeholder Registry | [5 empty] | VAKIANIS KYRIAKOS |  | : Prepared by
Date: | 2025-03-30 | [9 empty] | 2 |  | : Version
Data entry |  |  |  |  | Assessment |  |  | Stakeholder |  | Handling / Follow up
Role | Contact Name | Category | Subcategory | Current Engagement | Interest | Influence / Power | Classification / Impact | Requirements by stakeholder | Expectations by stakeholder | Actions / Communication | Desired Engagement | Contingency Plans: if response is ineffective | Status
S1 | Starlight Medical Center Management | External | Sponsor | Supportive | 5 | 5 | 25 | Succesful digital transition that enhances efficiency, complies with regulations, and showcases measurable improvements | Strategic alignment, measurable ROI, minimal disruptions, smooth implementation, ongoing technical support, staff compliance, long-term sustainability. | Regular progress meetings, executive reports, strategic alignment sessions, decision-making involvement. | Leading | Adjust project KPIs to align with their strategic goals, increase meeting frequency | Monitoring
S2 | Medical Center IT Department | External | Functional manager | Resistant | 4 | 4 | 16 | Seamless integration with existing infrastructure, clear documentation, compliance with IT policies and structured maintenance processes | Continuous updates, efficient troubleshooting, , seamless user experience, minimal system downtime, training for internal teams. | Technical workshops, system integration testing, direct collaboration with DigitalMed IT team, security briefings | Supportive | Provide additional technical support, hands-on training, and incease involvment in development to reduce resistance | Monitoring
S3 | Doctors / Medical Staff | External | User | Resistant | 5 | 3 | 15 | User-friendly interface, fast EHR access, AI-driven decision support, error reduction, seamless workflow integration, training resources | Increased efficiency, reduced administrative workload, reliable system performance, responsive IT support, enhanced diagnostic accuracy | Role-specific training programs, usability testing, feedback collection, interactive Q&A sessions. | Supportive | If resistance grows, appoint department representatives to advocate, adjust interface design, and involve staff in testing | Action taken
S4 | Medical Center Executive Board | External | Board of Executives | Neutral | 4 | 5 | 20 | Cost justification, compliance assurance, operational impact analysis and metrics, risk assessment, clear implementation strategy | Transparent reporting, alignment with strategic goals, measurable benefits, smooth transition, regulatory compliance, return on investment, positive hospital reputation | High-level reports, investment impact analysis, quarterly reviews, compliance briefings | Leading | Provide stronger ROI evidence, and regulatory risk assessments to justify project value and increase engagement | Monitoring
S5 | Patients | External | Patients | Resistant | 3 | 2 | 6 | Data security, accurate and fast medical services, efficient appointment scheduling and a reliable telemedicine experience. | Enhanced healthcare experience, improved doctor-patient communication, quick issue resolution, strong data protection, intuitive user interfaces, reduced bureaucracy | Awareness campaigns, user guides, telemedicine support , satisfaction surveys, public webinars | Supportive | Simplify access and invest in intuitive design and educational materials if feedback indicates confusion or mistrust. | Under assessment
S6 | DigitalMed Project Management | Internal | Team | Leading | 5 | 5 | 25 | Efficient resource use, stakeholder alignment, adherence to timetable and budget, decision-making for contigencies, and an overall succesful project | Timely approvals, stakeholder cooperation, adherence to project deadlines, proactive issue resolution, stable budget allocation | Transparent executive summaries, frequent project tracking dashboards, stakeholder briefings, risk management sessions | Leading | Restructure project roles, increase oversight, and escalate issues to senior leadership for decision-making | Monitoring
S7 | IT Consultants | External | Other | Neutral | 3 | 3 | 9 | Detailed system architecture, clear project scope, well-defined technical difficulties | Clear communication, responsive feedback, timely decision-making, access to relevant hospital IT teams | External audits, best practice recommendations, integration validation, support and solution-integration sessions | Neutral | If performance issues arise, reassess vendor selection and establish stronger accountability mechanisms | Action taken
S8 | DigitalMed Trainers | Internal | Team | Neutral | 3 | 2 | 6 | Comprehensive training materials, scenario-based learning, interactive modules, ongoing support channels | High staff engagement, positive training outcomes, smooth system onboarding, accessible resources | Hands-on workshops, e-learning modules, role-specific training materials | Supportive | If training impact is low, introduce adaptive learning techniques and expand training durations | Action taken
S9 | DigitalMed IT Dpt | Internal | Supplier | Supportive | 5 | 4 | 20 | Clarity in tasks, realistic timelines, and easy access to all tools needed | Timely feedback from hospital IT teams, structured deployment phases, clear technical documentation, minimal system conflicts, compliance verification | Agile development updates, bug tracking reports, system testing feedback loops, cybersecurity briefings | Supportive | Increase resource allocation, prioritize critical system updates, and introduce dedicated on-site IT support | Monitoring
S10 | Regulatory Authorities | External | Regulatory Body | Resistant | 3 | 5 | 15 | Full HIPAA/GDPR compliance, patient data protection, secure data storage, reporting transparency, ethical AI use | Periodic compliance reports, responsive regulatory audits, secure system access protocols, data security | Compliance reports, periodic audits, legal consultations, security framework adherence documentation | Neutral | If regulatory pushback occurs, engage legal teams and revise compliance strategies | Under assessment
S11 | Medical Center Data Governance Officer | External | Functional manager | Resistant | 4 | 4 | 16 | Data privacy compliance, secure access controls, robust cybersecurity sstem, accurate reporting | Transparent data policies, collaboration with IT teams, regulatory alignment, minimal data breaches | Schedule regular briefings, provide access logs, ensure risk mitigation strategy alignment. | Supportive | Reinforce data governance responsibilities and provide ensurance for data security and regulation adherence | Action taken
S12 | DigitalMed Financial Dpt | Internal | Team | Neutral | 3 | 3 | 9 | Realistic system requirements, contingency fund management, cost efficiency strategies | Clear financial reporting, on-budget execution, optimized resource allocation, justification of expenses | Budget reports, ROI forecasts, cost-benefit analysis meetings, financial risk assessments | Supportive | Restructure financial planning and discuss alternative solutions and requirement planning in case of resistance | Monitoring

## Stakeholder Matrix
Power
|  | 1 | 2 | 3 | 4 | 5
Interest |  | Insignificant | Minor | Moderate | Significant | Severe | Status | Description
5 | Very High | Low Medium | Medium | Medium High | High | High | New | Newly identified
4 | High | Low | Low Medium | Medium | Medium High | High | Under assessment | Actions taken to assess the stakeholder
3 | Medium | Low | Low Medium | Medium | Medium High | Medium High | Action taken | Assessed and action taken
2 | Low | Low | Low Medium | Low Medium | Medium | Medium High | Monitoring | Assessed, action taken and under monitoring
1 | Very Low | Low | Low | Low Medium | Low | Low | Closed | No longer a stakeholder with impact
Rating / Classification
|  | 1 | 2 | 3 | 4 | 5
5 |  | 5 | 10 | 15 | 20 | 25
4 |  | 4 | 8 | 12 | 16 | 20
3 |  | 3 | 6 | 9 | 12 | 15
2 |  | 2 | 4 | 6 | 8 | 10
1 |  | 1 | 2 | 3 | 4 | 5