## Risk Register
Step 1 Identification - Description |  | Step 2 Assessment |  |  | Step 3 Response (mitigate, transfer, avoidance, accept) | Step 2 Assessment / Step 4 Monitoring |  |  | Contingency / Workaround
|  | Severity prior to action |  |  |  | Severity after response
Time | Brief description | Probability | Impact | Rating | Response Handling | Probability | Impact | Rating | Contingency Plans: if response is ineffective | Status | Owner
S1 | System integration delays (due to compatibility issues) | 3 | 4 | 12 | Mitigate - Active Monitoring and prior testing | 2 | 3 | 6 | Consult system manufacturers / Develop infrastrucure from scratch | New: requires action plan | IT team
S2 | Delays in regulatory approval (due to slow compliance checks) | 2 | 4 | 8 | Mitigate - Early engagement with regulatory authorities | 1 | 2 | 2 | Assign Compliance Team to accelerate approval process | Active: monitoring | Compliance and Legal Team
Quality | Brief description | Probability | Impact | Rating | Response Handling | Probability | Impact | Rating | Contingency Plans | Status | Owner
Q1 | Technical failures (S/W and H/W malfunctions) | 4 | 4 | 16 | Mitigate - Implement manual backup systems and emergency protocols | 3 | 3 | 9 | Seek consultation from 3rd party | Actions complete: monitor | IT team
Q2 | Cybersecurity threats | 4 | 5 | 20 | Mitigate - Implement multi-layer security (firewalls, encryption, MFA) to reduce the likelihood of a breach. | 2 | 4 | 8 | Restore data from backups / Notify authorities for security breach | Actions complete: monitor | IT team, Legal team
Q3 | Inadequate Testing Procedures | 3 | 4 | 12 | Mitigate - Implement comprehensive testing at each development milestone to ensure quality. | 2 | 3 | 6 | Increase testing resources or outsource to specialized firms if internal measures fail. | Actions in progress | IT team
Q4 | Defective Deliverables Due to Inadequate Review | 4 | 4 | 16 | Mitigate - Implement peer reviews and checklist-based quality audits before final delivery. | 2 | 3 | 6 | Escalate to senior quality management and introduce additional QA cycles if needed. | Actions in progress | Quality Assurance Supervisor
Cost | Brief description | Probability | Impact | Rating | Response Handling | Probability | Impact | Rating | Contingency Plans | Status | Owner
C1 | Budget Overruns | 3 | 4 | 12 | Mitigate - contigency fund and continuous financial monitoring | 2 | 3 | 6 | Adjust project scope / request for budget increase | Actions complete: monitor | Finance team
C2 | Unexpected Maintenance and Support Costs | 2 | 4 | 8 | Mitigate - Implement preventive system monitoring to detect issues before they escalate | 1 | 4 | 4 | Postpone non-critical upgrades to reallocate funds for urgent fixes | New: requires action plan | Finance team
Technical | Brief description | Probability | Impact | Rating | Response Handling | Probability | Impact | Rating | Contingency Plans | Status | Owner
T1 | Software Integration Failure | 3 | 4 | 12 | Mitiate - Conduct frequent integration tests and use version control best practices. | 2 | 3 | 6 | Engage external consultants if issues persist. | New: requires action plan | IT Team
T2 | Hardware Failures in Critical Systems | 3 | 4 | 12 | Mitiate - Conduct frequent integration tests and use version control best practices. | 2 | 3 | 6 | Keep swappable backups on-site; maintain service agreements with hardware vendors. | Action: Monitoring | IT Team
Other | Brief description | Probability | Impact | Rating | Response Handling | Probability | Impact | Rating | Contingency Plans | Status | Owner
O1 | Employee resistance to change | 3 | 4 | 12 | Mitigate - comprehensive training and user-friendly design | 2 | 3 | 6 | One-on-one training sessions / ongoing support | Actions in progress | HR / training team
O2 | Patient adoption of telemedicine | 2 | 4 | 8 | Transfer - let medical center HR team to deal with it | 1 | 3 | 3 | Make system changes to enhance acceptance | Actions complete: closed | Medical Center's HR team
O3 | Non - compliance with regulations | 2 | 4 | 8 | Avoid - take all necessary actions to meet all regulatory requirements | 1 | 3 | 1 | None - risk avoided | Actions complete: closed | Compliance and Legal Team
Organizational | Brief description | Probability | Impact | Rating | Response Handling | Probability | Impact | Rating | Contingency Plans | Status | Owner
OR1 | Insufficient Training for Team | 4 | 3 | 12 | Transfer - Hire external trainers or e-learning platforms. | 2 | 2 | 4 | Hire external trainers or e-learning platforms. | Active: monitoring | HR / training team
OR2 | High Staff Turnover During Project | 3 | 4 | 12 | Mitigate - Improve staff retention via incentives, career growth opportunities, and feedback loops | 2 | 3 | 6 | Prepare succession plans and cross-train key team members to prevent disruptions | Active: monitoring | HR

## Risk Matrix
Impact
|  | 1 | 2 | 3 | 4 | 5
Probability |  | Insignificant | Minor | Moderate | Significant | Severe | Risk Status | Description
5 | Very Likely | Low Medium | Medium | Medium High | High | High | Active: monitoring | Risk event still possible
4 | Likely | Low | Low Medium | Medium | Medium High | High | New: requires action plan | Newly identified risk
3 | Possible | Low | Low Medium | Medium | Medium High | Medium High | Actions complete: monitor | Risk manifested and actions taken to manage the risk
2 | Unlikely | Low | Low Medium | Low Medium | Medium | Medium High | Actions in progress | Risk manifested, action being taken
1 | Very Unlikely | Low | Low | Low Medium | Medium | Medium | Actions complete: closed | Risk manifested, actions taken, risk no longer a threat
[7 empty] | Closed | Risk not longer a threat
|  | 1 | 2 | 3 | 4 | 5
|  | Insignificant | Minor | Moderate | Significant | Severe | Owner
5 | Very Likely | 2 | 3 | 4 | 5 | 5 | Assign roles & delegate
4 | Likely | 1 | 2 | 3 | 4 | 5
3 | Possible | 1 | 2 | 3 | 4 | 4
2 | Unlikely | 1 | 2 | 2 | 3 | 4
1 | Very Unlikely | 1 | 1 | 2 | 3 | 3
Proposed Risk Management matrix
Rating
|  | 5 | 10 | 15 | 20 | 25
|  | 4 | 8 | 12 | 16 | 20
|  | 3 | 6 | 9 | 12 | 15
|  | 2 | 4 | 6 | 8 | 10
|  | 1 | 2 | 3 | 4 | 5